## Plan
Details
Project Name | APRNet
Mentor | Joel Jonsson
Project Start | 15.04.2019
Duration | 12 Weeks
Project End (Actual) | 08.07.2019
Buffer | 1 Month
Project End | 05.08.2019
Team Members
Bhasker, Nithya
Fareed, Fahad
Güttner, Bianca
Invernizzi, Leonardo
Timeline
15.04.2019 | 29.04.2019 -09.06.2019 | 09.06.2019 – 18.06.2019 | 18.06.2019 – 12.07.2019 | 12.07.2019 – 01.08.2019 | 05.08.2019 (Tentative)
Kick Off | Literature Survey And Concept Design | Implementation – Upsampling | Implementation – Segmentation | Project Report | Project Presentation

## OPL
Task | Start Date | Responsible | Updates | Due Date | Today | End Date
Read Joel’s Thesis | 2019-05-24 | Bianca |  | 2019-04-29 | 2019-06-19 | 2019-06-19
Read Joel’s Thesis | 2019-05-24 | Fahad |  | 2019-04-29 | 2019-06-19 | 2019-06-19
Read Joel’s Thesis | 2019-05-24 | Leonardo |  | 2019-04-29 | 2019-06-19 | 2019-06-19
Read Joel’s Thesis | 2019-05-24 | Nithya |  | 2019-04-29 | 2019-06-19 | 2019-06-19
ask for his code (thesis) | 2019-04-29 | all |  | 2019-08-05 | 2019-06-19
get an overview on upsampling | 2019-04-29 | all |  | 2019-05-02 | 2019-06-19
skeleton for the project report (format) |  |  |  |  | 2019-06-19
skeleton for the project report (content list) |  |  |  |  | 2019-06-19
add references to BibTeX + short summary | 2019-04-29 | all |  | 2019-05-02 | 2019-06-19
put this file into github | 2019-04-29 | Fahad |  |  | 2019-06-19 | 2019-05-01
create a github account | 2019-04-29 | all except Fahad, Nithya |  |  | 2019-06-19
Conventional methods for upsampling, share summary | 2019-06-19 | Fahad |  | 2019-05-08 | 2019-06-19
Other methods for upsampling, share summary | 2019-06-19 | Leonardo |  | 2019-05-08 | 2019-06-19
Other methods+transposed convolution, share summary | 2019-06-19 | Bianca |  | 2019-05-08 | 2019-06-19
Transposed convolution, share summary | 2019-06-19 | Nithya |  | 2019-05-08 | 2019-06-19
Schedule a meeting with Joel | 2019-06-19 | Bianca |  |  | 2019-06-19 | 2019-05-02
Upload the .bib file on Github | 2019-06-19 | Nithya |  | 2019-05-08 | 2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19
2019-06-19

## Appendix
Voraussetzungen für
die Vergabe von Leis-
tungspunkten
Die Leistungspunkte werden erworben, wenn die Modulprüfung
bestanden ist. Die Modulprüfung besteht aus einer Projektarbeit im
Umfang von 12 Wochen, eines Projektberichts von 80 Stunden und
einem Kolloquium von 30 Minuten.
Leistungspunkte und
Noten
Durch das Modul können 10 Leistungspunkte erworben werden. Die
Modulnote ergibt sich aus dem ungewichteten Durchschnitt der
Noten der Prüfungsleistungen.
Häufigkeit des Mod-
uls
Das Modul wird jedes Sommersemester angeboten.
Arbeitsaufwand Der Arbeitsaufwand beträgt insgesamt 300 Stunden.

## Questions
After implementing the upsampling, what should be the problem that we test it on?
How does the network (APRnet) look like? (pooling, activation, conv layers – how many? Where?)

## Concepts
- tensorflow
- his GitHub
- Pytorch
- LibAPR

## Reviews and Meetings
Date | Type | Status
2019-04-29 | Internal Meeting | Done
2019-05-02 | Internal Meeting | Done
2019-05-10 | Review with Joel | Done
2019-05-24 | Internal Meeting | Done
2019-06-03 | Internal Meeting | Done
2019-06-11 | Internal Meeting | Done
2019-06-19 | Internal Meeting
2019-06-21 | Review with Joel
2019-06-26 | Internal Meeting
2019-07-03 | Internal Meeting
2019-07-10 | Internal Meeting
Review with Joel (Final implementation)
Internal Meeting (Finalize project report)
Internal Meeting (Finalize project report)